## PA1 tasks
| Start | End
PA1 | 2024-10-20 | 2024-11-02
Task | Assign | Start | Deadline | Status
Write project plan section 1 | Hưng | 2024-10-22 | 2024-10-27 | Done
Write project plan section 2 | Hưng | 2024-10-22 | 2024-10-27 | Done
Write project plan section 3 | Bảo | 2024-10-22 | 2024-10-27 | Done
Write project plan section 4.1 | Nhân | 2024-10-22 | 2024-10-27 | Done
Write project plan section 4.2 | Nhân | 2024-10-22 | 2024-10-27 | Done
Write project plan section 4.3 | Lạc | 2024-10-22 | 2024-10-27 | Done
Write vision document section 1 | Nhân | 2024-10-27 | 2024-11-01 | Done
Write vision document section 2 | Nhân | 2024-10-27 | 2024-11-01 | Done
Write vision document section 3 | Bảo | 2024-10-27 | 2024-11-01 | Done
Write vision document section 4 | Lạc | 2024-10-27 | 2024-11-01 | Done
Write vision document section 5 | Lạc | 2024-10-27 | 2024-11-01 | Done
Write vision document section 6 | Hưng | 2024-10-27 | 2024-11-01 | Done
Learn Express, Mongoose | Everyone | 2024-10-20 | 2024-11-02 | Done

## PA2 tasks
| Start | End
PA2 | 2024-11-03 | 2024-11-16
Task | Assign | Start | Deadline | Status
Each member fix their respective section in PA1
Revise project plan | Everyone | 2024-11-03 | 2024-11-16 | Done
Revise vision document | Everyone | 2024-11-03 | 2024-11-16 | Done
Model use-case access (login/logout/register) | Lạc | 2024-11-03 | 2024-11-06 | Done
Model use-case search for manga | Lạc | 2024-11-03 | 2024-11-06 | Done
Model use-case manage library | Nhân | 2024-11-03 | 2024-11-06 | Done
Model use-case interact manga (read/report/comment) | Hưng | 2024-11-03 | 2024-11-06 | Done
Model use-case manage user reports | Nhân | 2024-11-03 | 2024-11-06 | Done
Model use-case manage users | Nhân | 2024-11-14 | 2024-11-16 | Done
Model use-case manage manga (upload/update/delete) | Bảo | 2024-11-03 | 2024-11-06 | Done
Specify use-case access (login/logout/register) | Lạc | 2024-11-06 | 2024-11-15 | Done
Specify use-case search for manga | Lạc | 2024-11-06 | 2024-11-15 | Done
Specify use-case manage library | Nhân | 2024-11-06 | 2024-11-15 | Done
Specify use-case interact manga (read/report/comment) | Hưng | 2024-11-06 | 2024-11-15 | Done
Specify use-case manage user reports | Nhân | 2024-11-06 | 2024-11-15 | Done
Model use-case manage users | Nhân | 2024-11-14 | 2024-11-16 | Done
Specify use-case manage manga (upload/update/delete) | Bảo | 2024-11-06 | 2024-11-15 | Done
Design the UI/UX | Hưng | 2024-11-03 | 2024-11-16 | Late
Design the UI/UX | Lạc | 2024-11-03 | 2024-11-16 | Late
Design the frontend | Bảo | 2024-11-08 | 2024-11-21 | Late
Design the backend | Nhân | 2024-11-03 | 2024-11-16 | Done
Learn React | Everyone | 2024-11-03 | 2024-11-16 | Done

## PA3 tasks
| Start | End
PA3 | 2024-11-17 | 2024-11-30
Task | Assign | Start | Deadline | Status
Each member fixs their respective use-case in PA2
Revise use-cases | Everyone | 2024-11-17 | 2024-11-19 | Done
Write SAD section 1 | Hưng | 2024-11-17 | 2024-11-19 | Done
Write SAD section 2 | Bảo | 2024-11-17 | 2024-11-19 | Done
Write SAD section 3 | Lạc | 2024-11-17 | 2024-11-19 | Done
Write SAD section 3 | Nhân | 2024-11-17 | 2024-11-19 | Done
Write logical view | Nhân | 2024-11-20 | 2024-11-30 | Done
Write component view | Bảo | 2024-11-20 | 2024-11-30 | Done
Write component model | Lạc | 2024-11-20 | 2024-11-30 | Done
Write component controller | Hưng | 2024-11-20 | 2024-11-30 | Done
Back End coding tasks
Create Back End folder structure | Nhân | 2024-11-17 | 2024-11-17 | Done
Code User APIs (/api/users) | Lạc | 2024-11-18 | 2024-11-22 | Done
Code Library APIs (/api/users/library) | Lạc | 2024-11-23 | 2024-11-27 | Done
Code Blacklist APIs (/api/users/blacklist) | Lạc | 2024-11-28 | 2024-12-03 | Done
Code BanUser APIs (/api/users/ban) | Bảo | 2024-11-18 | 2024-11-22 | Done
Code UserNotification APIs (/api/users/notifications) | Bảo | 2024-11-23 | 2024-11-27 | Done
Code ReadingHistory APIs (/api/mangas/:id/readingHistory) | Bảo | 2024-11-28 | 2024-12-03 | Done
Code Author APIs (/api/authors) | Hưng | 2024-11-18 | 2024-11-22 | Done
Code Category APIs (/api/categories) | Hưng | 2024-11-23 | 2024-11-27 | Done
Code Report APIs (/api/reports) | Hưng | 2024-11-28 | 2024-12-03 | Done
Code Manga APIs (/api/mangas) | Nhân | 2024-11-18 | 2024-11-22 | Done
Code Chapter APIs (/api/mangas/:id/chapters) | Nhân | 2024-11-23 | 2024-11-27 | Done
Code Cover APIs (/api/mangas/:id/covers) | Nhân | 2024-11-28 | 2024-12-03 | Done
Front End coding tasks
Create Front End folder structure | Nhân | 2024-11-24 | 2024-11-25 | Done
Code Navigation bar | Hưng | 2024-11-22 | 2024-11-25 | Done
Code Homepage (display recent updated and top rated mangas) | Bảo | 2024-11-26 | 2024-11-29 | Done
Code Manga's details page (title, authors, gernes, chapters...) | Nhân | 2024-11-22 | 2024-11-25 | Done
Code Reading chapter page (long strip mode) | Nhân | 2024-11-26 | 2024-11-29 | Done
Code Search page + Search result page (has filter option) | Hưng | 2024-11-26 | 2024-11-29 | Done
Code User library page | Lạc | 2024-11-22 | 2024-11-25 | Done
Code Login/Register page | Lạc | 2024-11-26 | 2024-11-29 | Done

## PA4 tasks
| Start | End
PA4 | 2024-12-01 | 2024-12-14
Task | Assign | Start | Deadline | Status
Each member fixs their respective section in PA3
Revise SAD | Everyone | 2024-12-01 | 2024-12-03 | Done
Adjust UI/UX design (if needed) | Hưng | 2024-12-01 | 2024-12-14 | Done
Adjust UI/UX design (if needed) | Lạc | 2024-12-01 | 2024-12-14 | Done
Adjust UI code (if needed) | Everyone | 2024-12-01 | 2024-12-19 | Done
Describe Navbar UI | Hưng | 2024-12-04 | 2024-12-14 | Done
Describe Homepage UI | Bảo | 2024-12-04 | 2024-12-14 | Done
Describe Manga Page UI | Nhân | 2024-12-04 | 2024-12-14 | Done
Describe Reading Chapter Page UI | Nhân | 2024-12-04 | 2024-12-14 | Done
Describe Search Page and Result UI | Hưng | 2024-12-04 | 2024-12-14 | Done
Describe User Library Page UI | Lạc | 2024-12-04 | 2024-12-14 | Done
Describe Login/Register Page UI | Lạc | 2024-12-04 | 2024-12-14 | Done
Describe Manga Management Page UI | Nhân | 2024-12-04 | 2024-12-14 | Done
Describe Report Management Page UI | Hưng | 2024-12-04 | 2024-12-14 | Done
Describe User Details Page UI | Lạc | 2024-12-04 | 2024-12-14 | Done
Describe Authors/Categories Management Page UI | Bảo | 2024-12-04 | 2024-12-14 | Done
Code Comment APIs (/api/mangas/:id/comments) | Nhân | 2024-12-04 | 2024-12-08 | Done
Code Search APIs (/api/search) | Hưng | 2024-12-04 | 2024-12-08 | Done
Code Manga management page (for approved user) | Nhân | 2024-11-30 | 2024-12-21 | Done
Code Report management page (for admins) | Hưng | 2024-11-30 | 2024-12-21 | Done
Code Edit User details page | Lạc | 2024-11-30 | 2024-12-21 | Done
Code Authors/Categories management page (for admins) | Bảo | 2024-11-30 | 2024-12-21 | Done
Code User management page | Nhân | 2024-11-30 | 2024-12-21 | Done
Code Publications Management Panel (for admins) | Nhân | 2024-11-30 | 2024-12-21 | Done

## PA5 tasks
| Start | End
PA5 | 2024-12-15 | TBA
Task | Assign | Start | Deadline | Status
Each member perform at least 5 test cases
At least 5 test cases for each feature (how)
At least 25 test cases for 5 different features
Fill out test plan | Lạc | 2024-12-15 | 2024-12-16 | Done
Fix bugs found in testing | Everyone | 2024-12-19 | 2024-12-26 | Done
Create test cases for Login/Signup | Lạc | 2024-12-16 | 2024-12-26 | Done
Create test cases for Edit Profile | Lạc | 2024-12-16 | 2024-12-26 | Done
Create test cases for Search Manga | Hưng | 2024-12-16 | 2024-12-26 | Done
Create test cases for Read Manga | Hưng | 2024-12-16 | 2024-12-26 | Done
Create test cases for Manage Manga | Nhân | 2024-12-16 | 2024-12-26 | Done
Create test cases for Interact with Manga | Nhân | 2024-12-16 | 2024-12-26 | Done
Create test cases for Report Manga | Bảo | 2024-12-16 | 2024-12-26 | Done
Create test cases for Manage User | Bảo | 2024-12-16 | 2024-12-26 | Done
Perform testing for Login/Signup | Lạc | 2024-12-16 | 2024-12-26 | Done
Perform testing for Edit Profile | Lạc | 2024-12-16 | 2024-12-26 | Done
Perform testing for Search Manga | Hưng | 2024-12-16 | 2024-12-26 | Done
Perform testing for Read Manga | Hưng | 2024-12-16 | 2024-12-26 | Done
Perform testing for Manage Manga | Nhân | 2024-12-16 | 2024-12-26 | Done
Perform testing for Interact with Manga | Nhân | 2024-12-16 | 2024-12-26 | Done
Perform testing for Report Manga | Bảo | 2024-12-16 | 2024-12-26 | Done
Perform testing for Manage User | Bảo | 2024-12-16 | 2024-12-26 | Done